## Sheet1
ID | Story | Estimated Hours | Priority (1-5) | Sprint When Finished
1 | Link together voice, cloud, and ROS system | 4 | 1 | 2
2 | Figure out how to use the microphone on the USB in the docker | 3 | 1 | 2
3 | Create handling for complex command scenarios (i.e. 2+ sequential commands) | 8 | 2 | 2
4 | Improve response latency by some means | 3 | 2 | 3
5 | Continuous listening | 5 | 2 | 2
6 | Create tests for basic command interpretation | 3 | 3 | 2
7 | Finish reverse engineering the WonderPi app | 5 | 3 | 2
GOALS
1. Give PuppyPi voice commands for action groups
2. Give PuppyPi voice commands for non-action-group actions
3. Complex command scenario support (interruptions, 2+ commands, etc)
4. Out of box functionality