## Sheet1
ID | Story | Estimated Hours | Priority (1-5) | Sprint When Finished
1 | Create website for Capstone Project | 2 | 3 | 1
2 | Enable WiFi service on PuppyPi | 1 | 1 | 1
3 | Create and configure API gateway for PuppyPi | 3 | 1 | 1
4 | Create Lambda-based Cloud Transcription Service (audio-to-text) | 3 | 1 | 1
5 | Create Lambda-based Command Interpreter (text-to-command) | 3 | 1 | 1
6 | Understand code structure & run a ROS program via VNC | 6 | 5 | 1
7 | Bypass docker/vim constraints | 4 | 1 | 1
8 | Create an automatic CI/CD pipeline with GitHub to the PuppyPi | 2 | 2 | 1
9 | Create a voice recording service w/ microphone | 3 | 2 | 1
10 | Link together voice, cloud, and ROS system | 4 | 2 | 2
11 | Figure out how to use the microphone on the USB in the docker | 3 | 2 | 2
12 | Create tests for basic command interpretation | 3 | 3 | 2
13 | Finish reverse engineering the WonderPi app | 5 | 1 | 2
14 | Create handling for complex command scenarios (i.e. 2+ sequential commands) | 6 | 2 | 2
15 | Improve response latency by some means | 3 | 1 | 3
16 | Change from wake-word based voice detection to "continuous listening" | 7 | 3 | 3
17 | Create handling for continuous thinking commands (i.e. "follow me!") | 7 | 3 | 3
18 | Implement logging for cloud services | 1 | 1 | 3
19 | Automate the rebuilding of the docker within the PuppyPi without breaking it again | 4 | 1 | 3
20 | Improve transcription accuracy with noise reduction techniques | 3 | 1 | 3
21 | Integrate LIDAR, touch sensor, and other components of the PuppyPi Pro | 6 | 1 | 3