## Sheet1
ID | Story | Estimated Hours | Priority (1-5) | Sprint When Finished
1 | Create website for Capstone Project | 2 | 3 | 1
2 | Enable WiFi service on PuppyPi | 1 | 1 | 1
3 | Create and configure API gateway for PuppyPi | 3 | 1 | 1
4 | Create Lambda-based Cloud Transcription Service (audio-to-text) | 3 | 1 | 1
5 | Create Lambda-based Command Interpreter (text-to-command) | 3 | 1 | 1
6 | Understand code structure & run a ROS program via VNC | 6 | 5 | 1
7 | Bypass docker/vim constraints | 4 | 1 | 1
8 | Create an automatic CI/CD pipeline with GitHub to the PuppyPi | 2 | 2 | 1
9 | Create a voice recording service w/ microphone | 3 | 2 | 1
GOALS
1. Develop our cloud infrastructure (audio-to-command service)
2. Create a basic ROS program that we can run on the PuppyPi
3. Create a voice-listening service that can detect and record audio from a wakeword
4. Establish convenience (i.e. automatic git pull, integration with VS code, etc...)