## Sheet1
ID | Story | Estimated Hours | Priority (1-5) | Sprint When Finished
1 | Implement "stop" command | 4 | 1 | 3
2 | Improve latency & transcription accuracy, implement noise reduction techniques | 6 | 1 | 3
3 | Create complete app functionality incl. camera, lidar, etc. | 10 | 2 | 3
4 | YOLOv8/computer vision | 14 | 2 | 3
5 | Implement interoperability with different networks | 4 | 2 | 3
6 | Implement "length of time" commands | 2 | 3 | 3
7 | Create handling for continuous thinking commands ("follow me") | 7 | 3 | 3
8 | Test commands/command interpretation | 5 | 3 | 3
GOALS
1. PuppyPi can be asked to stop at any time, clearing the queue
2. PuppyPi has full app command list & additional commands
3. More foolproof latency & noise
4. YOLOv8/computer vision